## Sheet1
MATAINANCE ITEM | GOAL | SUPERPLOTS | 2013 TIMING | 2014 TIMING | GENERAL TIMING | FREQUENCY | APPROX TIME EFFORT | APPROX PEOPLE EFFORT | NEEDED SUPPLIES | NOTES | RESPONSIBILITY
Woody Resurvey | size measurments of tagged TR and SA, survey for status change of individuals (e.g. alive --> dead, SA --> TR) | n/a | Spring | na | NA | 5 Years | Months | 4 minimum | ropes, stakes, DBH tapes, measuring tapes, calipers, datasheets, pens, GPS |  | UNKNOWN
Mortality Survey | survey for mortality of tagged TR and SA | ? | August 3-7 | 8/15-9/15 | Late August/early September - end of dry season | Annual | 3 days | 4 | ropes, stakes, survey sheets, pens, GPS |  | OLDFATHER
SE/JU Surveys | survey for number of SE and JU individuals at the quad level of each plot | ? | Spring |  | May or August | Annual | 3 days | 4 | ropes, stakes, survey sheet, pens, GPS | Although in 2013 the survey for young individuals was during plot establishment, a specific week every year would be better - allow for oak seedlings to leaf out already | OLDFATHER
Canopy Measurements | take 6 canopy cover photos; 4 intrenal plot points (B2, B3, C3, C2), 1 center, 1 at HOBO | portion DEC | May 8-15 | Jan, June 9-20 | Early June, January | Bi-annual | 10 days (3-4 hours per day) | 2 (1 staff, 1 vol) | ropes, stakes, survey sheets, pens, GPS, concave densiometer, LIA meter? | Should consider switching to LAI meter instead of densiometer so comparison across years in more reliable | PEPPERWOOD
Soil Moisture Measurements | soil moisture measurment in each quad | yes | May 3-4 | Meagan? | Early May, Early September? (sync with mortality), Early January | Tri-annual? | 3 days | 2 | ropes, stakes, datasheet, pens, GPS, Hydrosense | Soil moisture was taken in 2013 only in May, but perhaps it should also be taken in late summer, as well mid-winter. | UNKNOWN
Percent Cover by Plot | survey the percent cover of bedrock, boulder, fine, soil, herb, litter at the quad level | n/a | Spring | na | NA | 5 years |  |  | ropes, stakes, datasheet, pens, GPS | This item needs to be discussed if annual or every 5 years, or if unnessary due to the more detailed herb surveys | UNKNOWN
Herbaceous Surveys | survey for the dominance of 'functional groupsat the plot level; creation of plot species lists | yes | Early June | na | Peak Biomass? Mid-Spring? Superplot | Annual |  |  | ropes, stakes, datasheets, pens, GPS |  | UNKNOWN
Hobo download | download climate data from each plot | n/a | NA | late March, June, October | June, October, Jan/Feb (synced with canopy cover) | Every 4 months | 3 days | 4 (2 staff, 2 vols) | Hobo shuttle, GPS |  | PEPPERWOOD
P/A of lichen | document the presence of absence of Ramalina, Usnea, and crustose/foliose lichens at each plot | yes | Early June | na |  | 5 Years |  |  | GPS, datasheet, pens | May want to consider a more comprehensive community sampling. | UNKNOWN
Fuel-moisture Sticks |  | yes | na |  | weekly, hottest time of day, Summer |  |  |  |  | Not sure the schedule or plan with these are? | UNKNOWN
Phenology |  | yes